## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 112 | 112
1 | 80 | 96
2 | 52 | 80
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 27 | 27
19 | 27 | 27
18 | 27 | 27
17 | 26 | 27
16 | 24 | 27
15 | 22 | 27
14 | 20 | 24
13 | 18 | 22
12 | 16 | 20
11 | 14 | 21
10 | 12 | 19
9 | 10 | 17
8 | 10 | 17
7 | 8 | 17
6 | 6 | 15
5 | 4 | 15
4 | 2 | 15
3 | 0 | 15
2 | 0 | 14
1 | 0 | 13
0 | 0 | 13
ALSO DO A SPRINT 2 BURNDOWN AS WELL
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 25 | 25
19 | 25 | 25
18 | 25 | 25
17 | 24 | 25
16 | 23 | 23
15 | 22 | 22
14 | 20 | 20
13 | 18 | 17
12 | 17 | 16
11 | 15 | 15
10 | 12 | 13
9 | 10 | 13
8 | 10 | 12
7 | 8 | 10
6 | 6 | 8
5 | 4 | 8
4 | 2 | 7
3 | 0 | 5
2 | 0 | 4
1 | 0 | 3
0 | 0 | 2